## Summary
AfrimaPesa V1.0 — Development Plan Tracker
Owner: Bruno Ganontha (CTO) · 16 weeks, 4 phases · Update the Status column on the Tasks and Exit Criteria sheets; everything here recalculates.
Project start date (Monday of Week 1) |  | 2026-09-28
Planned launch (end of Week 16) |  | 2027-01-15
Today |  | 2026-09-25
Current project week |  | Not started
Phase | Name | Weeks | Start | End | Tasks | Done | In progress | Blocked | % Tasks done | Exit criteria | Criteria met | % Criteria met
Phase 1 | Infrastructure & Remittance Engine | 1–4 | 2026-09-28 | 2026-10-23 | 13 | 0 | 0 | 0 | 0% | 5 | 0 | 0%
Phase 2 | Commercial Banking & Admin | 5–8 | 2026-10-26 | 2026-11-20 | 13 | 0 | 0 | 0 | 0% | 4 | 0 | 0%
Phase 3 | Sovereign Yield Tracker | 9–12 | 2026-11-23 | 2026-12-18 | 11 | 0 | 0 | 0 | 0% | 4 | 0 | 0%
Phase 4 | Integration, Hardening & Launch | 13–16 | 2026-12-21 | 2027-01-15 | 14 | 0 | 0 | 0 | 0% | 5 | 0 | 0%
Total |  |  |  |  | 51 | 0 | 0 | 0 | 0% | 18 | 0 | 0%
Open decisions & risks |  | 9
Legend
Yellow cell with blue text = input you can edit. Status columns use dropdowns. Rows turn green when Done/Met and red when Blocked.
Note on C4: Input: assumed Monday 28 Sep 2026. Change this and all task dates on the Tasks sheet shift.

## Tasks
ID | Phase | Week | Workstream | Task | Deliverable / Demo | Start | End | Status | Owner | Notes
T01 | Phase 1 | 1 | Infrastructure | Set up monorepo (backend/, ingestion/, frontend/, infra/) and Docker Compose for local dev | docker compose up starts full stack | 2026-09-28 | 2026-10-02 | Not started | Bruno
T02 | Phase 1 | 1 | Infrastructure | Configure GitHub Actions CI: lint, type checks, tests | CI green on main | 2026-09-28 | 2026-10-02 | Not started | Bruno
T03 | Phase 1 | 1 | Infrastructure | Provision dev + staging environments, managed Postgres/TimescaleDB and Redis | Staging reachable | 2026-09-28 | 2026-10-02 | Not started | Bruno
T04 | Phase 1 | 2 | Data model | Create reference tables: countries, currencies, corridors (seed 18), providers, user preferences | Migrations run cleanly | 2026-10-05 | 2026-10-09 | Not started | Bruno
T05 | Phase 1 | 2 | Data model | Create hypertables fx_mid_rates and provider_quotes, plus ingestion_runs table | Schema reviewed | 2026-10-05 | 2026-10-09 | Not started | Bruno
T06 | Phase 1 | 2 | Remittance | Build calculation engine: F_transfer, A_net, effective rate, top-5 ranking by A_net | Unit tests incl. fee edge cases | 2026-10-05 | 2026-10-09 | Not started | Bruno
T07 | Phase 1 | 2 | Remittance | Start mid-market FX ingestion every 5 minutes for all 18 corridors | Rates landing in DB | 2026-10-05 | 2026-10-09 | Not started | Bruno
T08 | Phase 1 | 3 | Ingestion | Build base adapter interface (fetch → normalize → validate → store) with retries/backoff | Framework merged | 2026-10-12 | 2026-10-16 | Not started | Bruno
T09 | Phase 1 | 3 | Ingestion | Log every run to ingestion_runs; add sanity validator rejecting quotes far from mid-market | Bad quotes rejected in tests | 2026-10-12 | 2026-10-16 | Not started | Bruno
T10 | Phase 1 | 3 | Remittance | Build Wise adapter (public API) | Wise quotes refresh on schedule | 2026-10-12 | 2026-10-16 | Not started | Bruno
T11 | Phase 1 | 4 | Remittance | Build Remitly adapter (Playwright) | Remitly quotes refresh on schedule | 2026-10-19 | 2026-10-23 | Not started | Bruno
T12 | Phase 1 | 4 | API | Build GET /v1/remittance/compare endpoint; cache quotes per corridor in Redis | p95 < 300 ms from cache | 2026-10-19 | 2026-10-23 | Not started | Bruno
T13 | Phase 1 | 4 | Frontend | Build minimal Next.js remittance comparison page | End-to-end demo in staging | 2026-10-19 | 2026-10-23 | Not started | Bruno
T14 | Phase 2 | 5 | Data model | Create banks, bank products, rate_observations hypertable and tenor normalization map | Migrations run cleanly | 2026-10-26 | 2026-10-30 | Not started | Bruno
T15 | Phase 2 | 5 | Banking | Implement APY and real-rate calculations (documented default compounding) | Unit tests pass | 2026-10-26 | 2026-10-30 | Not started | Bruno
T16 | Phase 2 | 5 | Data | Add CPI inflation ingestion for all 6 countries | CPI data in DB | 2026-10-26 | 2026-10-30 | Not started | Bruno
T17 | Phase 2 | 5 | Data | Build bank source inventory (HTML / PDF / not published) for ~29 banks | Inventory complete; phase re-sized | 2026-10-26 | 2026-10-30 | Not started | Bruno
T18 | Phase 2 | 6 | Ingestion | Build reusable HTML and PDF (pdfplumber) scraper templates | Templates merged | 2026-11-02 | 2026-11-06 | Not started | Bruno
T19 | Phase 2 | 6 | Banking | Scrapers for first batch of banks (~3 countries) | Rates from 3 countries in DB | 2026-11-02 | 2026-11-06 | Not started | Bruno
T20 | Phase 2 | 7 | Banking | Scrapers for remaining 3 countries; mark non-publishing banks as 'manual' source | All 6 countries have data | 2026-11-09 | 2026-11-13 | Not started | Bruno
T21 | Phase 2 | 7 | Remittance | Build WorldRemit and Western Union adapters (carry-over) | Quotes refresh on schedule | 2026-11-09 | 2026-11-13 | Not started | Bruno
T22 | Phase 2 | 8 | Admin | Admin authentication with 2FA and roles (admin, editor) | Login works with 2FA | 2026-11-16 | 2026-11-20 | Not started | Bruno
T23 | Phase 2 | 8 | Admin | Manual rate override form with required reason field | Override updates public page | 2026-11-16 | 2026-11-20 | Not started | Bruno
T24 | Phase 2 | 8 | Admin | Append-only audit log enforced at DB level (revoked UPDATE/DELETE, trigger) | Test proves rows immutable | 2026-11-16 | 2026-11-20 | Not started | Bruno
T25 | Phase 2 | 8 | Admin | Scraper health dashboard + Slack/email alert after 2 consecutive failures | Broken scraper visible & alerted | 2026-11-16 | 2026-11-20 | Not started | Bruno
T26 | Phase 2 | 8 | Frontend | Public banking page: country selector, lending/deposit tabs, sortable columns | Page live in staging | 2026-11-16 | 2026-11-20 | Not started | Bruno
T27 | Phase 3 | 9 | Data model | Create instruments table and yield_observations hypertable | Migrations run cleanly | 2026-11-23 | 2026-11-27 | Not started | Bruno
T28 | Phase 3 | 9 | Admin | Add credit rating entry (S&P, Fitch, Moody's) to admin panel | Ratings editable & audited | 2026-11-23 | 2026-11-27 | Not started | Bruno
T29 | Phase 3 | 9 | Data | Decide Eurobond price source (paid feed vs delayed public data) | Decision recorded | 2026-11-23 | 2026-11-27 | Not started | Bruno
T30 | Phase 3 | 10 | Sovereign | Build T-bill and bond auction scrapers for 6 countries (PDF-heavy) | Latest auctions ingested | 2026-11-30 | 2026-12-04 | Not started | Bruno
T31 | Phase 3 | 10 | Sovereign | Implement discount-to-yield with per-country day-count conventions | Unit tests pass | 2026-11-30 | 2026-12-04 | Not started | Bruno
T32 | Phase 3 | 10 | Sovereign | Implement YTM from price with numerical solver (Brent) | Matches references within 1 bp | 2026-11-30 | 2026-12-04 | Not started | Bruno
T33 | Phase 3 | 11 | Sovereign | Fit Nelson-Siegel curves per country/date with cubic spline fallback; store params | Curves generated | 2026-12-07 | 2026-12-11 | Not started | Bruno
T34 | Phase 3 | 11 | Sovereign | Compute real yields: (1 + YTM) / (1 + inflation) − 1 | Unit tests pass | 2026-12-07 | 2026-12-11 | Not started | Bruno
T35 | Phase 3 | 11 | Sovereign | Validate curves against published ones (e.g. FMDQ, JSE) | Fit error within threshold | 2026-12-07 | 2026-12-11 | Not started | Bruno
T36 | Phase 3 | 12 | Frontend | Sovereign page: yield curve chart (Recharts), T-bill/bond/Eurobond tables, ratings matrix, history | Page live in staging | 2026-12-14 | 2026-12-18 | Not started | Bruno
T37 | Phase 3 | 12 | Remittance | Add LemFi, NALA, Sendwave, Chipper, Flutterwave (prefer partner APIs) | Quotes refresh on schedule | 2026-12-14 | 2026-12-18 | Not started | Bruno
T38 | Phase 4 | 13 | Frontend | Global country/region preference (cookie + profile) | Preference persists across pages | 2026-12-21 | 2026-12-25 | Not started | Bruno
T39 | Phase 4 | 13 | Frontend | Notification sign-up with double opt-in and UK GDPR consent records | Consent stored | 2026-12-21 | 2026-12-25 | Not started | Bruno
T40 | Phase 4 | 13 | Frontend | Site-wide FX ticker | Ticker live | 2026-12-21 | 2026-12-25 | Not started | Bruno
T41 | Phase 4 | 13 | QA | Playwright end-to-end tests for 3 core user journeys | E2E suite green in CI | 2026-12-21 | 2026-12-25 | Not started | Bruno
T42 | Phase 4 | 14 | Performance | Locust load tests (target 500 concurrent users, p95 < 500 ms) | Load test report | 2026-12-28 | 2027-01-01 | Not started | Bruno
T43 | Phase 4 | 14 | Performance | Database index review | Slow queries resolved | 2026-12-28 | 2027-01-01 | Not started | Bruno
T44 | Phase 4 | 14 | Performance | TimescaleDB continuous aggregates and compression; tune Redis TTLs | Historical charts fast | 2026-12-28 | 2027-01-01 | Not started | Bruno
T45 | Phase 4 | 15 | Security | OWASP Top 10 review; dependency and container scanning; secrets manager | No high-severity findings | 2027-01-04 | 2027-01-08 | Not started | Bruno
T46 | Phase 4 | 15 | Security | Admin behind IP allowlist/VPN + 2FA; rate limiting and WAF | Controls verified | 2027-01-04 | 2027-01-08 | Not started | Bruno
T47 | Phase 4 | 15 | Security | Backup and restore drill (actually restore) | Restore succeeded | 2027-01-04 | 2027-01-08 | Not started | Bruno
T48 | Phase 4 | 16 | DevOps | Terraform infrastructure as code | Prod reproducible from code | 2027-01-11 | 2027-01-15 | Not started | Bruno
T49 | Phase 4 | 16 | DevOps | ECS deployment with blue/green releases; rehearse rollback | Rollback rehearsed | 2027-01-11 | 2027-01-15 | Not started | Bruno
T50 | Phase 4 | 16 | DevOps | Monitoring (Sentry, CloudWatch/Grafana) and scraper-failure runbooks | Alerts firing correctly | 2027-01-11 | 2027-01-15 | Not started | Bruno
T51 | Phase 4 | 16 | Launch | Soft launch | V1.0 live | 2027-01-11 | 2027-01-15 | Not started | Bruno
Formulas:
Start = Summary!$C4+7*([Week]-1)
End = [Start]+4

## Exit Criteria
ID | Phase | Criterion | Target / Test | Status | Evidence / Link | Date verified
E01 | Phase 1 | Mid-market FX refresh | All 18 corridors refresh at least every 5 minutes | Not met
E02 | Phase 1 | Provider ingestion reliability | Wise & Remitly: ≥95% successful runs over 3 days | Not met
E03 | Phase 1 | Compare API latency | p95 < 300 ms served from cache | Not met
E04 | Phase 1 | Calculation engine tests | ≥90% test coverage | Not met
E05 | Phase 1 | Stale data flagging | Quotes older than 2× update interval flagged in API | Not met
E06 | Phase 2 | Bank coverage | ≥80% of tracked banks show ≥1 deposit and ≥1 lending product | Not met
E07 | Phase 2 | Source transparency | Every displayed rate shows source and last-verified date | Not met
E08 | Phase 2 | Audit log integrity | Automated test proves audit rows cannot be modified | Not met
E09 | Phase 2 | Scraper monitoring | Broken scraper shown within 1 run and alert fired | Not met
E10 | Phase 3 | Auction freshness | Latest auction per country ingested within 24 h of publication | Not met
E11 | Phase 3 | Yield curves | Curves generated when ≥4 tenor points; sparse curves labelled | Not met
E12 | Phase 3 | YTM accuracy | YTM within 1 bp of reference examples | Not met
E13 | Phase 3 | Credit ratings | All 6 sovereigns × 3 agencies entered with date and source | Not met
E14 | Phase 4 | Load testing | Agreed load targets met (default 500 users, p95 < 500 ms) | Not met
E15 | Phase 4 | Security | No open high-severity findings | Not met
E16 | Phase 4 | Disaster recovery | Restore from backup tested successfully | Not met
E17 | Phase 4 | Observability | Monitoring and alerts live in production | Not met
E18 | Phase 4 | Rollback | Rollback rehearsed at least once | Not met

## Decisions & Risks
ID | Type | Item | Impact on | Needed by | Owner | Status | Resolution / Notes
D01 | Decision | Cloud provider (AWS recommended, since Phase 4 targets ECS) | Infrastructure choices | Before Week 1 | Bruno + Claudio | Open
D02 | Decision | Mid-market FX data source (paid FX API) | Remittance reference rate and ticker | Before Week 1 | Bruno + Claudio | Open
D03 | Decision | Legal position on scraping and reverse-engineered APIs | Provider adapters | Before Week 1 | Claudio | Open
D04 | Decision | MVP cut line if schedule slips | Launch date | Before Week 1 | Bruno + Claudio | Open
D05 | Gap | Pillar 4 (expert commentary), notifications and news feed not in roadmap; news needs Reuters/Bloomberg licensing | Scope / launch date | Before Week 1 | Claudio | Open
D06 | Risk | Scraping / app API reverse engineering likely breaches provider ToS; fragile. Mitigate: UK legal advice, affiliate/partner programs | Remittance module | Before Phase 1 ends | Claudio | Open
D07 | Risk | 'Real-time' sovereign data unrealistic: T-bills are weekly/biweekly auctions; live Eurobond prices need paid feed | User expectations / budget | Week 9 | Bruno + Claudio | Open
D08 | Risk | Many banks publish no rates online (esp. lending) — needs ongoing manual collection by operations | Banking coverage / staffing | Week 5 | Claudio | Open
D09 | Risk | 16 weeks tight for one developer covering ~40 data sources | Launch date | Ongoing | Bruno | Open